## Slide 1: COMMUNITY DEVELOPMENT COMMISSION OF THE COUNTY OF LOS ANGELES 700 W. Main St., Alhambra CA 91801 www.lacdc.org
It's About Timeliness!

## Slide 2: Some Facts About L.A. County
The largest Urban County program in the nation in terms of dollars…$23.4M currently
Large number of subrecipients…
  48 participating small cities
  25 non-profits
  10 County Departments
$4.6M Admin budget, 23 staff
Timely every year but one in 35 years

## Slide 3: Effective Grant Administration = Timeliness
Strong administrative structure puts everybody on the same page.
Clearly defined cycle calendared from planning through expenditure of funds – communicated internally and externally.
Delineate and communicate policies and procedures and give them teeth!
Regular recurrent training for subrecipients on grant management.

## Slide 4: Effective Grant Administration = Timeliness
Develop system to “flag” slow projects early on (before IDIS does) – look for administrative warning signs.
Build project timelines into contracts, monitor through performance reporting.
Try to track as close as possible to real time – is annual monitoring after the fact enough?
Consider in-progress monitoring to track progress.
Ensure that agencies are “capable” from the start and able to handle the rigors of grant funding.
Invoke a “use-it-or-lose-it” mentality through penalty budgeting or recapture policies.

## Slide 5
If a subrecipient doesn’t have capacity, they won’t be able to effectively spend the money!
New agencies need to be reviewed for program/financial capacity before the contract is let.
Have a structured process in place that allows feedback to make corrections.
Be able to discern between critical and minor concerns to move forward with contract.
Importance of Capacity Reviews

## Slide 6: Capacity Reviews (cont’d)
Conduct capacity reviews to cover both program and financial capacity.
Program Capacity – What to look for…
  Adequate method for collecting client documents and data
  Organized filing systems
  Minimum equipment needed to conduct business with you – scanners, copiers, computers, high speed internet access
Financial Capacity – Accounting System Review
  Double-entry accounting system
  Internal controls, separation of duties
  General ledger with separate cost centers
  Tracking of program income
  Regular reconciliation of bank statements

## Slide 7: Checklists allow consistency

## Slide 9: “Use it or lose it” – Recapturing Funds
Participating cities receive about half of Urban County allocation for their projects.
Performance Policy developed when HUD made timeliness more stringent through sanctions.
Sought “buy-in” to policy by having a city work group assist with policy development.
  Carrot – recaptured funds would be redistributed to “timely” cities on a competitive basis.

## Slide 10: Keys to a Successful and “Low-Grief” Recapture Process
Written policy that clearly identifies process and deadlines.
Notify agencies early and frequently of expenditure status.
Warn agency executive management of impending deadline and implications.
Allow an appeals process before recapturing funds.
  Include peers on appeals panel.

## Slide 11: Sample Tracking Report

## Slide 12: Keys to a Successful and “Low-Grief” Recapture Process – Cont’d
Build flexibility into potential outcomes from appeals
  Allow exchange of funds between cities
  No recapture based on successful appeal
  Partial recapture based on circumstances
  Deferred recapture with promise to expend by deadlines
  Full recapture – “Frequent Flyer”
Have a method to recapture that won’t disrupt existing projects.

## Slide 13
Some Other Ideas
Set up a revolving grant fund for subreceipients to free up excess money
  Functions like a mini Section 108 loan program without interest costs.
  Excess money from subrecipients put in, to be borrowed by others with a more immediate need.
  Money repaid by future allocations – our participating cities receive annual formula allocations and repay from this.

## Slide 14
…And a Couple More
Contribute Excess Funding to Priority Efforts
  Participating cities can contribute excess funds directly homeless programs that we operate to help with that regional effort
Properly manage any revolving loan funds to make sure the amount of funds in the pool match the level of loan activity.

## Slide 15: With These Tools and a Little Luck…

## Slide 16
Questions?
We Build Better Lives & Better Neighborhoods
Scott.Stevenson@lacdc.org